## Kaavish I & II
GANTT CHART
| Task | Member | Completion | Kaavish I | [13 empty] | Kaavish II
|  |  |  | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12 | WEEK 13 | WEEK 14 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12 | WEEK 13 | WEEK 14 | WEEK 15
1 | Project Proposal
1.1 | Background Research | Everyone | 100% | bar: Kaavish I WEEK 1 to Kaavish I WEEK 3
1.2 | Idea Formulation | Everyone | 100% | bar: Kaavish I WEEK 1 to Kaavish I WEEK 3
1.3 | Proposal Writing | Everyone | 100% | bar: Kaavish I WEEK 2 to Kaavish I WEEK 3
1.4 | Proposal Submission | Everyone | 100% | bar: Kaavish I WEEK 3
2 | Literature Review & Revision
2.1 | Protein-Protein Interactions (PPI) | Ali | 60% | bar: Kaavish I WEEK 2 to Kaavish I WEEK 8
2.2 | PPI Networks | Ali | 50% | bar: Kaavish I WEEK 2 to Kaavish I WEEK 10
2.3 | Analysis Techniques | Usaid | 70% | bar: Kaavish I WEEK 6 to Kaavish I WEEK 10
2.4 | Ensemble Framework | Haris | 30% | bar: Kaavish I WEEK 7 to Kaavish I WEEK 10
2.5 | Clustering Algorithms | Usaid/Haris | 25% | bar: Kaavish I WEEK 8 to Kaavish I WEEK 10
2.6 | Prediction Methods | Usaid/Haris | 15% | bar: Kaavish I WEEK 9 to Kaavish I WEEK 10
3 | Dataset Collection
3.01 | Find Sources for Datasets | Maham | 80% | bar: Kaavish I WEEK 6 to Kaavish I WEEK 10
3.02 | Collect PPIN Data Files | Maham | 40% | bar: Kaavish I WEEK 8 to Kaavish I WEEK 13
3.03 | Methods to Parse Files | Usaid | 30% | bar: Kaavish I WEEK 10 to Kaavish I WEEK 14
3.04 | Preprocess the data | Ali/Haris | 0% | bar: Kaavish I WEEK 11 to Kaavish I WEEK 14
3.05 | Create Standard Format | Maham | 0% | bar: Kaavish I WEEK 11 to Kaavish I WEEK 14
3.06 | Convert to Standard Format | Ali | 0% | bar: Kaavish I WEEK 11 to Kaavish I WEEK 14
3.07 | Methods to Read/Write SF Files | Usaid | 0% | bar: Kaavish I WEEK 11 to Kaavish I WEEK 14
3.08 | Create Protein Dataset | Maham | 0% | bar: Kaavish I WEEK 11 to Kaavish I WEEK 14
3.09 | Write Methods to Interface with Protien Dataset | Ali/Usaid | 0% | bar: Kaavish I WEEK 11 to Kaavish I WEEK 14
4 | SRS Documentation
4.1 | Introduction | Ali | 100% | bar: Kaavish I WEEK 11
4.2 | Literature Review | Usaid/Haris/Ali | 100% | bar: Kaavish I WEEK 4 to Kaavish I WEEK 10
4.3 | Functional Requirements | Ali | 100% | bar: Kaavish I WEEK 7 to Kaavish I WEEK 11
4.4 | External Interfaces | Haris | 100% | bar: Kaavish I WEEK 9 to Kaavish I WEEK 11
4.5 | Dataset | Maham | 100% | bar: Kaavish I WEEK 6 to Kaavish I WEEK 10
4.6 | Gantt Chart | Ali/Haris | 100% | bar: Kaavish I WEEK 11
5 | SDS Documentation
5.1 | Proposed System Model | Usaid | 0% | bar: Kaavish I WEEK 12 to Kaavish I WEEK 14
5.2 | Architecture Diagram | Ali | 0% | bar: Kaavish I WEEK 12 to Kaavish I WEEK 14
5.3 | Updated Literature Review | Haris/Maham | 0% | bar: Kaavish I WEEK 12 to Kaavish I WEEK 14
5.4 | Evaluation Metrics | Maham | 0% | bar: Kaavish I WEEK 12 to Kaavish I WEEK 14
7 | Code
7.1 | Data Interfacing Class | Maham/Ali | 0%
7.2 | PPIN Class | Everyone | 0%
7.3 | Analysis Techniques Implementation | Haris/Usaid | 0%
7.4 | Prediction Method Implementation | Haris/Usaid/Ali | 0%
8 | Prediction Algorithm
8.1 | Compare Available Methods | Usaid | 0%
8.2 | Find Candidate Methods for Ensemble Method | Usaid/Haris | 0%
8.3 | Design Prototype Ensemble Method | Ali/Usaid | 0%
8.4 | Code Prototype Ensemble Method | Haris/Ali | 0%
9 | Visualization
9.1 | Design Visualizer using preexisting tools | Usaid/Ali | 0%
9.2 | API to connect visualizer to output data | Haris | 0%
9.3 | Test Visualizer | Usaid/Ali/Haris | 0%
10 | Testing & Debugging
10.1 | Fine Tune Results | Haris/Usaid | 0%
10.2 | Clean Codebase & Document Code | Maham | 0%
10.3 | Debug and Test Code | Ali | 0%
11 | Final Report | bar: Kaavish I WEEK 1 to Kaavish II WEEK 10
11.1 | Compile Results and Research | Usaid | 0% | bar: Kaavish II WEEK 11 to Kaavish II WEEK 15
11.2 | Write Report | Allen W | 0%
11.3 | Edit Report | Malik M | 0%